Problem 2

Develop a network diagram for the project specified below:

| Activity | Immediate Predecessor Activity |
| --- | --- |
| A | - |
| B | A |
| C, D | B |
| E | C |
| F | D |
| G | E, F |

Solution

Activity A has no predecessor activity. i.e., It is the first activity. Let  us suppose that activity A takes the project from event 1 to event 2. Then  we have the following representation for A:

A

1 2

For activity B, the predecessor activity is A. Let us suppose that B

joins nodes 2 and 3. Thus we get

A B

1 2 3

Activities C and D have B as the predecessor activity. Therefore we  obtain the following:

247

B

2 3

C D

4

5

Activity E has D as the predecessor activity. So we get

C E

3 4 6

Activity F has D as the predecessor activity. So we get

D F

3 5 6l

”

Activity G has E and F as predecessor activities. This is possible  only if nodes 6 and 6l are one and the same. So, rename node 6l as node 6.  Then we get

D F

3 5 6! and

4

G

6 7

5

E

F

248

G is the last activity.

Putting all the pieces together, we obtain the following diagram the  project network:

4

C E

Start event End event

A B

2 3

1

D F

5

G

6 7

The diagram is validated by referring to the given data.

Note: An important point may be observed for the above diagram.  Consider the following parts in the diagram

C E

3 4 6

and

D F

3 5 6l”

We took nodes 6 and 6l as one and the same. Instead, we can retain  them as different nodes. Then, in order to provide connectivity to the  network, we join nodes 6l and 6 by a dummy activity. Then we arrive at  the following diagram for the project network:

Start event 1

4

C

2 3

E

dummy

6

G

A B

D

activity

7

5

F

6l !

End event

249

Questions

1. Explain the terms: event, predecessor event, successor event, activity,  dummy activity, network.

2. Construct the network diagram for the following project:

| Activity | Immediate Predecessor Activity |
| --- | --- |
| A | - |
| B | - |
| C | A |
| D | B |
| E | A |
| F | C, D |
| G | E |
| H | E |
| I | F, G |
| J | H, I |

****

250

Lesson 4 - Critical Path Method (CPM)

Lesson Outline

ӹ The concepts of critical path and critical activities

ӹ Location of the critical path

ӹ Evaluation of the project completion time

Learning Objectives

After reading this lesson you should be able to

ӹ understand the definitions of critical path and critical activities ӹ identify critical path and critical activities

ӹ determine the project completion time

Introduction

The critical path method (CPM) aims at the determination of the  time to complete a project and the important activities on which a manager  shall focus attention.

Assumption For Cpm

In CPM, it is assumed that precise time estimate is available for  each activity.

Project Completion Time

From the start event to the end event, the time required to complete  all the activities of the project in the specified sequence is known as the  project completion time.

251

Path In A Project

A continuous sequence, consisting of nodes and activities  alternatively, beginning with the start event and stopping at the end event  of a network is called a path in the network.

Critical Path And Crtical Activities

Consider all the paths in a project, beginning with the start  event and stopping at the end event. For each path, calculate the time of  execution, by adding the time for the individual activities in that path.

The path with the largest time is called the critical path and the  activities along this path are called the critical activities or bottleneck  activities. The activities are called critical because they cannot be delayed.  However, a non-critical activity may be delayed to a certain extent. Any  delay in a critical activity will delay the completion of the whole project.  However, a certain permissible delay in a non –critical activity will not  delay the completion of the whole project. It shall be noted that delay in a  non-critical activity beyond a limit would certainly delay the completion  the whole project. Sometimes, there may be several critical paths for a  project. A project manager shall pay special attention to critical activities.

Problem 1

The following details are available regarding a project:

| Activity | Predecessor Activity | Duration (Weeks) |
| --- | --- | --- |
| A | - | 3 |
| B | A | 5 |
| C | A | 7 |
| D | B | 10 |
| E | C | 5 |
| F | D,E | 4 |

252

Determine the critical path, the critical activities and the project  completion time.

Solution

First let us construct the network diagram for the given project. We  mark the time estimates along the arrows representing the activities. We  obtain the following diagram:

Start event

End event

A

B

5

3

D

10

1 2 3

7CE5 4

F

5 6 4

Consider the paths, beginning with the start node and stopping  with the end node. There are two such paths for the given project. They are  as follows:

Path I

A B D F

1 2 3 5 6 3 5 10 4

with a time of 3 + 5 + 10 + 4 = 22 weeks.

Path II

A C E F

1 2 4 5 6 3 7 5 4

with a time of 3 + 7 + 5 + 4 = 19 weeks.

Compare the times for the two paths. Maximum of {22,19} = 22.  We see that path I has the maximum time of 22 weeks. Therefore, path  I is the critical path. The critical activities are A, B, D and F. The project

253

completion time is 22 weeks.

We notice that C and E are non- critical activities.

Time for path I - Time for path II = 22- 19 = 3 weeks.

Therefore, together the non- critical activities can be delayed upto  a maximum of 3 weeks, without delaying the completion of the whole  project.

Problem 2

Find out the completion time and the critical activities for the  following project:

A

8

D

2

B

5

20G 8

1

E

H 11 K 6

1

7

C

10

3

16

6 1

I

J

14

8

1

9

L

5

10

4

Solution

F 10

1

7

25

In all, we identify 4 paths, beginning with the start node of 1 and  terminating at the end node of 10. They are as follows:

Path I

A D G K

1 2 5 8 10 8 20 8 6

Time for the path = 8 + 20 + 8 + 6 = 42 units of time.

254

Path II

B E H K

1 3 6 8 10 10 16 11 6

Time for the path = 10 + 16 + 11 + 6 = 43 units of time. Path III

B E I L

1 3 6 9 10 10 16 14 5

Time for the path = 10 + 16 + 14 + 5 = 45 units of time. Path IV

1 4 7 9 10

C F J L

7 25 10 5

Time for the path = 7 + 25 + 10 + 5 = 47 units of time.

Compare the times for the four paths. Maximum of {42,  43, 45, 47} = 47. We see that the following path has the maximum  time and so it is the critical path:

1 4 7 9 10

C F J L

7 25 10 5

The critical activities are C, F, J and L. The non-critical activities  are A, B, D, E, G, H, I and K. The project completion time is 47  units of time.

Problem 3

255

Draw the network diagram and determine the critical path for the  following project:

| Activity | Time estimate (Weeks) |
| --- | --- |
| 1- 2 | 5 |
| 1- 3 | 6 |
| 1- 4 | 3 |
| 2 -5 | 5 |
| 3 -6 | 7 |
| 3 -7 | 10 |
| 4 -7 | 4 |
| 5 -8 | 2 |
| 6 -8 | 5 |
| 7 -9 | 6 |
| 8 -9 | 4 |

Solution

We have the following network diagram for the project:

A

D

5

H

1

2

5

2

5

1

B 6

3

E 7

6 1

I

3

8

K

4

C 3

G

10

F

7

19 1

J

6

4

4

256

Solution

We assert that there are 4 paths, beginning with the start node of 1  and terminating at the end node of 9. They are as follows:

Path I

A D H K

1 2 5 8 9 5 5 2 4

Time for the path = 5 + 5 + 2 + 4 = 16 weeks.

Path II

B E I K

1 3 6 8 9 6 7 5 4

Time for the path = 6 + 7 + 5 + 4 = 22 weeks.

Path III

1 3 7 9

B F J

6 10 6

Time for the path = 6 + 10 + 6 = 16 weeks.

Path IV

1 4 7 9

C 4 5

3 4 6

Time for the path = 3 + 4 + 6 = 13 weeks.

Compare the times for the four paths. Maximum of {16, 22, 16, 13}  = 22. We see that the following path has the maximum time and so it is the  critical path:

257

D E I K

1 3 6 8 9 6 7 5 4

The critical activities are B, E, I and K. The non-critical activities are A, C,  D, F, G, H and J. The project completion time is 22 weeks.

Questions

1. Explain the terms: critical path, critical activities.

2. The following are the time estimates and the precedence relationships  of the activities in a project network:

| Activity | IMMEDIATE Predecessor Activity | time estimate (weeks) |
| --- | --- | --- |
| A | - | 4 |
| B | - | 7 |
| C | - | 3 |
| D | A | 6 |
| E | B | 4 |
| F | B | 7 |
| G | C | 6 |
| H | E | 10 |
| I | D | 3 |
| J | F, G | 4 |
| K | H, I | 2 |

Draw the project network diagram. Determine the critical path and the  project completion time.

****

258

Lesson 5 - Pert

Lesson Outline

ӹ The Concept Of Pert

ӹ Estimates Of The Time Of An Activity

ӹ Determination Of Critical Path

ӹ Probability Estimates

ӹ Normal Probability Distribution Table

Learning Objectives

After reading this lesson you should be able to

ӹ Understand the importance of PERT

ӹ Locate the critical path

ӹ Determine the project completion time

ӹ Find out the probability of completion of a project before a  stipulated time

ӹ Use the normal probability distribution table

Introduction

Programme Evaluation and Review Technique (PERT) is a tool that  would help a project manager in project planning and control. It would  enable him in continuously monitoring a project and taking corrective  measures wherever necessary. This technique involves statistical methods.

Assumptions for Pert

Note that in CPM, the assumption is that precise time estimate is  available for each activity in a project. However, one finds most of the  times that this is not practically possible.

259

In PERT, we assume that it is not possible to have precise time  estimate for each activity and instead, probabilistic estimates of time  alone are possible. A multiple time estimate approach is followed here. In  probabilistic time estimate, the following 3 types of estimate are possible:

Pessimistic time estimate ( p t )

Optimistic time estimate ( ot )

Most likely time estimate ( mt )

The optimistic estimate of time is based on the assumption that  an activity will not involve any difficulty during execution and it can be  completed within a short period. On the other hand, a pessimistic estimate  is made on the assumption that there would be unexpected problems  during the execution of an activity and hence it would consume more  time. The most likely time estimate is made in between the optimistic and  the pessimistic estimates of time. Thus the three estimates of time have the  relationship

om p ttt ≤ ≤

Practically speaking, neither the pessimistic nor the optimistic  estimate may hold in reality and it is the most likely time estimate that is  expected to prevail in almost all cases. Therefore, it is preferable to give  more weight to the most likely time estimate.

We give a weight of 4 to most likely time estimate and a weight of 1  each to the pessimistic and optimistic time estimates. We arrive at a time  estimate ( et ) as the weighted average of these estimates as follows: t++ =

t tt

4

o mp

e

6

Since we have taken 6 units ( 1 for p t , 4 for mt and 1 for ot ), we  divide the sum by 6. With this time estimate, we can determine the project  completion time as applicable for CPM.

Since PERT involves the average of three estimates of time for each  activity, this method is very practical and the results from PERT will be  have a reasonable amount of reliability.

260

Measure Of Certainty

The 3 estimates of time are such that

om p ttt ≤ ≤

Therefore the range for the time estimate is po tt − .

The time taken by an activity in a project network follows  a distribution with a standard deviation of one sixth of the range,  approximately.

σ − =

po tt

i.e., The standard deviation = 6

2

σ − =  

2

and the variance =

po tt 6

The certainty of the time estimate of an activity can be analysed with  the help of the variance. The greater the variance, the more uncertainty in  the time estimate of an activity.

Problem 1

Two experts A and B examined an activity and arrived at the  following time estimates.

| Expert | Time Estimate |  |  |
| --- | --- | --- | --- |
|  | ot | mt | p t |
| A | 4 | 6 | 8 |
| B | 4 | 7 | 10 |

Determine which expert is more certain about his estimates of  time:

Solution

Variance ( 2 σ ) in time estimates =

po  tt −  6

2

261

In the case of expert A, the variance =

2

 −  = 

84 4 69

2

As regards expert B, the variance =

 −  = 

10 4 1 6

So, the variance is less in the case of A. Hence, it is concluded that  the expert A is more certain about his estimates of time.

Determination of Project Completion Time in PERT

Problem 2

Find out the time required to complete the following project and

the critical activities:

| Activity | Predecessor Activity | Optimistic time estimate (to days) | Most likely time estimate (tm days) | Pessimistic time estimate (tp days) |
| --- | --- | --- | --- | --- |
| A | - | 2 | 4 | 6 |
| B | A | 3 | 6 | 9 |
| C | A | 8 | 10 | 12 |
| D | B | 9 | 12 | 15 |
| E | C | 8 | 9 | 10 |
| F | D, E | 16 | 21 | 26 |
| G | D, E | 19 | 22 | 25 |
| H | F | 2 | 5 | 8 |
| I | G | 1 | 3 | 5 |

Solution

From the three time estimates p t , mt and ot , calculate et for each  activity. We obtain the following table:

262

| Activity | Optimistic time estimate (to) | 4 x Most likely time estimate | Pessimistic time estimate (tp) | to+ 4tm + tp | Time estimate t++ = t tt 4 o mp e 6 |
| --- | --- | --- | --- | --- | --- |
| A | 2 | 16 | 6 | 24 | 4 |
| B | 3 | 24 | 9 | 36 | 6 |
| C | 8 | 40 | 12 | 60 | 10 |
| D | 9 | 48 | 15 | 72 | 12 |
| E | 8 | 36 | 10 | 54 | 9 |
| F | 16 | 84 | 26 | 126 | 21 |
| G | 19 | 88 | 25 | 132 | 22 |
| H | 2 | 20 | 8 | 30 | 5 |
| I | 1 | 12 | 5 | 18 | 3 |

Using the single time estimates of the activities, we get the  following network diagram for the project.

3

A

1 2 4

B F215

6

6 12

I

5

8

10 E

4

22 3

9

7

Consider the paths, beginning with the start node and stopping  with the end node. There are four such paths for the given project. They  are as follows:

263

Path I A

B

D

F H

1 2 3 5 6 8

4

6

12

21

5

Time for the path: 4+6+12+21+5 = 48 days. Path II

A

B

D

G I

2 3 5 8 1 7

4

6

12

3 6 6

Time for the path: 4+6+12+ 6+3 = 31 days. Path III

A

C

E

F H

2 8 4 5

1 6

4

10

3

9

5 21 7

Time for the path: 4+10+9+ 21+5 = 49 days. Path IV

C

E

G I

2 4 5 8 A

1 7 3 6

4

10

9

6

Time for the path: 4+10+9+ 6+3 = 32 days.

Compare the times for the four paths.

Maximum of {48, 31, 49, 32} = 49.

We see that Path III has the maximum time.

Therefore the critical path is Path III. i.e., 1 2 4 5 6 8. The critical activities are A, C, E, F and H.

The non-critical activities are B, D, G and I.

Project time (Also called project length) = 49 days.

Problem 3

Find out the time, variance and standard deviation of the project  with the following time estimates in weeks:

264

| Activity | Optimistic time estimate (to) | Most likely time estimate (tm) | Pessimistic time estimate (tp) |
| --- | --- | --- | --- |
| 1-2 | 3 | 6 | 9 |
| 1-6 | 2 | 5 | 8 |
| 2-3 | 6 | 12 | 18 |
| 2-4 | 4 | 5 | 6 |
| 3-5 | 8 | 11 | 14 |
| 4-5 | 3 | 7 | 11 |
| 6-7 | 3 | 9 | 15 |
| 5-8 | 2 | 4 | 6 |
| 7-8 | 8 | 16 | 18 |

Solution

From the three time estimates p t , mt and ot , calculate et for each  activity. We obtain the following table:

| Activity | Optimistic time stimate (to) | 4 x Most likely time estimate | Pessimistic time estimate (tp) | to+ 4tm + tp | Time estimate t++ = t tt 4 o mp e 6 |
| --- | --- | --- | --- | --- | --- |
| 1-2 | 3 | 24 | 9 | 36 | 6 |
| 1-6 | 2 | 20 | 8 | 30 | 5 |
| 2-3 | 6 | 48 | 18 | 72 | 12 |
| 2-4 | 4 | 20 | 6 | 30 | 5 |
| 3-5 | 8 | 44 | 14 | 66 | 11 |

265

| 4-5 | 3 | 28 | 11 | 42 | 7 |
| --- | --- | --- | --- | --- | --- |
| 6-7 | 3 | 36 | 15 | 54 | 9 |
| 5-8 | 2 | 16 | 6 | 24 | 4 |
| 7-8 | 8 | 64 | 18 | 90 | 15 |

With the single time estimates of the activities, we get the following  network diagram for the project.

2

C

12

3

F

11

G

5

A

6

1

B

5 7 4

4

H

8

5 E

6

7

9

15

Consider the paths, beginning with the start node and stopping with the  end node. There are three such paths for the given project. They are as  follows:

Path I

A

C

F

I

1 2 3 5 8

6

12

11

4

Time for the path: 6+12+11+4 = 33 weeks. Path II

A

D

G

I

1 4 5 8 2

6

5

3

7

4

Time for the path: 6+5+7+ 4= 22 weeks. Path III

266

B

E

H

1 7 8

6

15

5

9

3

Time for the path: 5+9+15 = 29 weeks.

Compare the times for the three paths.

Maximum of {33, 22, 29} = 33.

It is noticed that Path I has the maximum time.

Therefore the critical path is Path I. i.e., 1 2 3 5 8

The critical activities are A, C, F and I.

The non-critical activities are B, D, G and H.

Project time = 33 weeks.

Calculation of Standard Deviation and Variance for the Critical  Activities:

| Critical Activity | Optimistic time estimate (to) | Most likely timeestimate (tm) | Pessimistic time estimate (tp) | Range (tp - to) | Standard deviation = σ − = po tt 6 | Variance 2 σ − =   po tt 2 6 |
| --- | --- | --- | --- | --- | --- | --- |
| A: 1 2 | 3 | 6 | 9 | 6 | 1 | 1 |
| C: 2 3 | 6 | 12 | 18 | 12 | 2 | 4 |
| F: 3 5 | 8 | 11 | 14 | 6 | 1 | 1 |
| I: 5 8 | 2 | 4 | 6 | 4 | 2/3 | 4/9 |

Variance of project time (Also called Variance of project length) =

Sum of the variances for the critical activities = 1+4+1+ 4/9 = 58/9 Weeks. Standard deviation of project time = √Variance = √58/9 = 2.54 weeks.

Problem 4

A project consists of seven activities with the following time

estimates. Find the probability that the project will be completed in 30  weeks or less.

267

| Activity | Predecessor Activity | Optimistic time estimate (to days) | Most likely time estimate (tm days) | Pessimistic time estimate (tp days) |
| --- | --- | --- | --- | --- |
| A | - | 2 | 5 | 8 |
| B | A | 2 | 3 | 4 |
| C | A | 6 | 8 | 10 |
| D | A | 2 | 4 | 6 |
| E | B | 2 | 6 | 10 |
| F | C | 6 | 7 | 8 |
| G | D, E, F | 6 | 8 | 10 |

Solution

From the three time estimates , and , calculate for each activity.  The results are furnished in the following table:

| Activity | Optimistic time estimate (to) | 4 x Most likely time estimate | Pessimistic time estimate (tp) | to+ 4tm + tp | Time estimate t++ = t tt 4 o mp e 6 |
| --- | --- | --- | --- | --- | --- |
| A | 2 | 20 | 8 | 30 | 5 |
| B | 2 | 12 | 4 | 18 | 3 |
| C | 6 | 32 | 10 | 48 | 8 |
| D | 2 | 16 | 6 | 24 | 4 |
| E | 2 | 24 | 10 | 36 | 6 |
| F | 6 | 28 | 8 | 42 | 7 |
| G | 6 | 32 | 10 | 48 | 8 |

With the single time estimates of the activities, the following  network diagram is constructed for the project.

3

B3

4

6

E

A

1 2 5

C

8

7

D

4

F

G

5 6 8

268

Consider the paths, beginning with the start node and stopping  with the end node. There are three such paths for the given project. They  are as follows:

Path I

1 6

A

2

B

E

3 5

G

5

3

4

6

8

8

Time for the path: 5+3+6+8 = 22 weeks.

Path II

A

C

F

4 5

G

1 6

5

2

8

4

7

8

8

Time for the path: 5+8+7+ 8 = 28 weeks.

Path III

A

D

G

1 5 6

5

2

4

4

8

Time for the path: 5+4+8 = 17 weeks.

Compare the times for the three paths.

Maximum of {22, 28, 17} = 28.

It is noticed that Path II has the maximum time.

Therefore the critical path is Path II. i.e., 1 2 4 5 6. The critical activities are A, C, F and G.

The non-critical activities are B, D and E.

Project time = 28 weeks.

Calculation of Standard Deviation and Variance for the  Critical Activities:

269

| Critical Activity | Optimistic time estimate (to) | Most likely time estimate (tm) | Pessimistic time estimate (tp) | Range (tp -to) | Standard deviation = σ − = po tt 6 | Variance 2 σ − =   po tt 2 6 |
| --- | --- | --- | --- | --- | --- | --- |
| A: 1 2 | 2 | 5 | 8 | 6 | 1 | 1 |
| C: 2 4 | 6 | 8 | 10 | 4 | 23 | 4 9 |
| F: 4 5 | 6 | 7 | 8 | 2 | 13 | 1 9 |
| G: 5 6 | 6 | 8 | 10 | 4 | 2 3 | 4 9 |

Standard deviation of the critical path = √2 = 1.414

The standard normal variate is given by the formula

Given value of t Expected value of t the critical in path ZSD for the critical path

− =

So we get 30 28

Z − = = 1.414

1.414

We refer to the Normal Probability Distribution Table.

Corresponding to Z = 1.414, we obtain the value of 0.4207

We get 0.5 + 0.4207 = 0. 9207

Therefore the required probability is 0.92

i.e., There is 92% chance that the project will be completed before 30 weeks.  In other words, the chance that it will be delayed beyond 30 weeks is 8%

270

Questions

1. Explain how time of an activity is estimated in PERT. 2. Explain the measure of certainty in PERT.

3. The estimates of time in weeks of the activities of a project are as  follows:

| Activity | Predecessor Activity | Optimistic estimate of time | Most likely estimate of time | Pessimistic estimate of time |
| --- | --- | --- | --- | --- |
| A | - | 2 | 4 | 6 |
| B | A | 8 | 11 | 20 |
| C | A | 10 | 15 | 20 |
| D | B | 12 | 18 | 24 |
| E | C | 8 | 13 | 24 |
| F | C | 4 | 7 | 16 |
| G | D,F | 14 | 18 | 28 |
| H | E | 10 | 12 | 14 |
| I | G,H | 7 | 10 | 19 |

Determine the critical activities and the project completion time.

4. Draw the network diagram for the following project. Determine the  time, variance and standard deviation of the project.:

271

| Activity | Predecessor Activity | Optimistic estimate of time | Most likely estimate of time | Pessimistic estimate of time |
| --- | --- | --- | --- | --- |
| A | - | 12 | 14 | 22 |
| B | - | 16 | 17 | 24 |
| C | A | 14 | 15 | 16 |
| D | A | 13 | 18 | 23 |
| E | B | 16 | 18 | 20 |
| F | D,E | 13 | 14 | 21 |
| G | C,F | 6 | 8 | 10 |

5. Consider the following project with the estimates of time in weeks:

| Activity | Predecessor Activity | Optimistic estimate of time | Most likely estimate of time | Pessimistic estimate of time |
| --- | --- | --- | --- | --- |
| A | - | 2 | 4 | 6 |
| B | - | 3 | 5 | 7 |
| C | A | 5 | 6 | 13 |
| D | A | 4 | 8 | 12 |
| E | B,C | 5 | 6 | 13 |
| F | D,E | 6 | 8 | 14 |

Find the probability that the project will be completed in 27 weeks.

272

NORMAL DISTRIBUTION TABLE

Area Under Standard Normal Distribution

|  | 0.00 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0.0 | 0.0000 | 0.0040 | 0.0080 | 0.0120 | 0.0160 | 0.0199 | 0.0239 | 0.0279 | 0.0319 | 0.0359 |
| 0.1 | 0.0398 | 0.0438 | 0.0478 | 0.0517 | 0.0557 | 0.0596 | 0.0636 | 0.0675 | 0.0714 | 0.0753 |
| 0.2 | 0.0793 | 0.0832 | 0.0871 | 0.0910 | 0.0948 | 0.0987 | 0.1026 | 0.1064 | 0.1103 | 0.1141 |
| 0.3 | 0.1179 | 0.1217 | 0.1255 | 0.1293 | 0.1331 | 0.1368 | 0.1406 | 0.1443 | 0.1480 | 0.1517 |
| 0.4 | 0.1554 | 0.1591 | 0.1628 | 0.1664 | 0.1700 | 0.1736 | 0.1772 | 0.1808 | 0.1844 | 0.1879 |
| 0.5 | 0.1915 | 0.1950 | 0.1985 | 0.2019 | 0.2054 | 0.2088 | 0.2123 | 0.2157 | 0.2190 | 0.2224 |
| 0.6 | 0.2257 | 0.2291 | 0.2324 | 0.2357 | 0.2389 | 0.2422 | 0.2454 | 0.2486 | 0.2517 | 0.2549 |
| 0.7 | 0.2580 | 0.2611 | 0.2642 | 0.2673 | 0.2704 | 0.2734 | 0.2764 | 0.2794 | 0.2823 | 0.2852 |
| 0.8 | 0.2881 | 0.2910 | 0.2939 | 0.2967 | 0.2995 | 0.3023 | 0.3051 | 0.3078 | 0.3106 | 0.3133 |
| 0.9 | 0.3159 | 0.3186 | 0.3212 | 0.3238 | 0.3264 | 0.3289 | 0.3315 | 0.3340 | 0.3365 | 0.3389 |
| 1.0 | 0.3413 | 0.3438 | 0.3461 | 0.3485 | 0.3508 | 0.3531 | 0.3554 | 0.3577 | 0.3599 | 0.3621 |
| 1.1 | 0.3643 | 0.3665 | 0.3686 | 0.3708 | 0.3729 | 0.3749 | 0.3770 | 0.3790 | 0.3810 | 0.3830 |
| 1.2 | 0.3849 | 0.3869 | 0.3888 | 0.3907 | 0.3925 | 0.3944 | 0.3962 | 0.3980 | 0.3997 | 0.4015 |
| 1.3 | 0.4032 | 0.4049 | 0.4066 | 0.4082 | 0.4099 | 0.4115 | 0.4131 | 0.4147 | 0.4162 | 0.4177 |
| 1.4 | 0.4192 | 0.4207 | 0.4222 | 0.4236 | 0.4251 | 0.4265 | 0.4279 | 0.4292 | 0.4306 | 0.4319 |
| 1.5 | 0.4332 | 0.4345 | 0.4357 | 0.4370 | 0.4382 | 0.4394 | 0.4406 | 0.4418 | 0.4429 | 0.4441 |
| 1.6 | 0.4452 | 0.4463 | 0.4474 | 0.4484 | 0.4495 | 0.4505 | 0.4515 | 0.4525 | 0.4535 | 0.4545 |
| 1.7 | 0.4554 | 0.4564 | 0.4573 | 0.4582 | 0.4591 | 0.4599 | 0.4608 | 0.4616 | 0.4625 | 0.4633 |
| 1.8 | 0.4641 | 0.4649 | 0.4656 | 0.4664 | 0.4671 | 0.4678 | 0.4686 | 0.4693 | 0.4699 | 0.4706 |
| 1.9 | 0.4713 | 0.4719 | 0.4726 | 0.4732 | 0.4738 | 0.4744 | 0.4750 | 0.4756 | 0.4761 | 0.4767 |
| 2.0 | 0.4772 | 0.4778 | 0.4783 | 0.4788 | 0.4793 | 0.4798 | 0.4803 | 0.4808 | 0.4812 | 0.4817 |

273

| 2.1 | 0.4821 | 0.4826 | 0.4830 | 0.4834 | 0.4838 | 0.4842 | 0.4846 | 0.4850 | 0.4854 | 0.4857 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.2 | 0.4861 | 0.4864 | 0.4868 | 0.4871 | 0.4875 | 0.4878 | 0.4881 | 0.4884 | 0.4887 | 0.4890 |
| 2.3 | 0.4893 | 0.4896 | 0.4898 | 0.4901 | 0.4904 | 0.4906 | 0.4909 | 0.4911 | 0.4913 | 0.4916 |
| 2.4 | 0.4918 | 0.4920 | 0.4922 | 0.4925 | 0.4927 | 0.4929 | 0.4931 | 0.4932 | 0.4934 | 0.4936 |
| 2.5 | 0.4938 | 0.4940 | 0.4941 | 0.4943 | 0.4945 | 0.4946 | 0.4948 | 0.4949 | 0.4951 | 0.4952 |
| 2.6 | 0.4953 | 0.4955 | 0.4956 | 0.4957 | 0.4959 | 0.4960 | 0.4961 | 0.4962 | 0.4963 | 0.4964 |
| 2.7 | 0.4965 | 0.4966 | 0.4967 | 0.4968 | 0.4969 | 0.4970 | 0.4971 | 0.4972 | 0.4973 | 0.4974 |
| 2.8 | 0.4974 | 0.4975 | 0.4976 | 0.4977 | 0.4977 | 0.4978 | 0.4979 | 0.4979 | 0.4980 | 0.4981 |
| 2.9 | 0.4981 | 0.4982 | 0.4982 | 0.4983 | 0.4984 | 0.4984 | 0.4985 | 0.4985 | 0.4986 | 0.4986 |
| 3.0 | 0.4987 | 0.4987 | 0.4987 | 0.4988 | 0.4988 | 0.4989 | 0.4989 | 0.4989 | 0.4990 | 0.4990 |

****

274

Lesson 6 - Earliest And Latest Times

Lesson Outline

ӹ The Concepts Of Earliest And Latest Times

ӹ The Concept Of Slack

ӹ Numerical Problems

Learning Objectives

ӹ After reading this lesson you should be able to

ӹ Understand the concepts of earliest and latest times

ӹ Understand the concept of slack

ӹ Calculate the earliest and latest times

ӹ Find out the slacks

ӹ Identify the critical activities

ӹ Carry out numerical problems

Introduction

A project manager has the responsibility to see that a project is  completed by the stipulated date, without delay. Attention is focused on  this aspect in what follows.

Key concepts

Certain key concepts are introduced below.

Earliest Times Of An Activity

We can consider (i) Earliest Start Time of an activity and (ii) Earliest  Finish Time of an activity.

275

Earliest Start Time of an activity is the earliest possible time of  starting that activity on the condition that all the other activities preceding  to it were began at the earliest possible times.

Earliest Finish Time of an activity is the earliest possible time of  completing that activity. It is given by the formula.

The Earliest Finish Time of an activity = The Earliest Start Time of  the activity + The estimated duration to carry out that activity.

LATEST TIMES OF AN ACTIVITY

We can consider (i) Latest Finish Time of an activity and (ii) Latest  Start Time of an activity.

Latest Finish Time of an activity is the latest possible time of  completing that activity on the condition that all the other activities  succeeding it are carried out as per the plan of the management and  without delaying the project beyond the stipulated time.

Latest Start Time of an activity is the latest possible time of  beginning that activity. It is given by the formula

Latest Start Time of an activity = The Latest Finish Time of the  activity - The estimated duration to carry out that activity.

TOTAL FLOAT OF AN ACTIVITY

Float seeks to measure how much delay is acceptable. It sets up a  control limit for delay.

The total float of an activity is the time by which that activity can  be delayed without delaying the whole project. It is given by the formula

Total Float of an Activity = Latest Finish Time of the activity -  Earliest Finish Time of that activity.

It is also given by the formula

Total Float of an Activity = Latest Start Time of the activity - Earliest

276

Start Time of that activity.

Since a delay in a critical activity will delay the execution of the  whole project, the total float of a critical activity must be zero.

EXPECTED TIMES OF AN EVENT

An event occurs at a point of time. We can consider (i) Earliest  Expected Time of Occurrence of an event and (ii) Latest Allowable Time  of Occurrence an event.

The Earliest Expected Time of Occurrence of an event is the earliest  possible time of expecting that event to happen on the condition that all  the preceding activities have been completed.

The Latest Allowable Time of Occurrence of an event is the latest  possible time of expecting that event to happen without delaying the  project beyond the stipulated time.

Procudure To Find The Earliest Expected Time Of An Event

Step 1

Take the Earliest Expected Time of Occurrence of the Start Event  as zero.

Step 2

For an event other than the Start Event, find out all paths in the  network which connect the Start node with the node representing the  event under consideration.

Step 3

In the “Forward Pass” (i.e., movement in the network from left to  right), find out the sum of the time durations of the activities in each path  identified in Step 2.

Step 4.

The path with the longest time in Step 3 gives the Earliest Expected  Time of Occurrence of the event

Working Rule for finding the earliest expected time of an event:

277

For an event under consideration, locate all the predecessor events  and identify their earliest expected times. With the earliest expected time  of each event, add the time duration of the activity connecting that event  to the event under consideration. The maximum among all these values  gives the Earliest Expected Time of Occurrence of the event.

Procudure To Find The Latest Allowable Time Of An Event

We consider the “Backward Pass” (i.e., movement in the network  from right to left).

The latest allowable time of occurrence of the End Node must be  the time of completion of the project. Therefore it shall be equal to the  time of the critical path of the project.

Step 1

Identify the latest allowable time of occurrence of the End Node.

Step 2

For an event other than the End Event, find out all paths in the  network which connect the End node with the node representing the event  under consideration.

Step 3

In the “Backward Pass” (i.e., movement in the network from right  to left), subtract the time durations of the activities along each such path.

Step 4

The Latest Allowable Time of Occurrence of the event is determined  by the path with the longest time in Step 3. In other words, the smallest  value of time obtained in Step 3 gives the Latest Allowable Time of  Occurrence of the event.

Working Rule for finding the latest allowable time of an event:

For an event under consideration, locate all the successor events  and identify their latest allowable times. From the latest allowable time of  each successor event, subtract the time duration of the activity that begins  with the event under consideration. The minimum among all these values

278

gives the Latest Allowable Time of Occurrence of the event. Slack Of An Event

The allowable time gap for the occurrence of an event is known as  the slack of that event. It is given by the formula

Slack of an event = Latest Allowable Time of Occurrence of the event -  Earliest Expected Time of Occurrence of that event.

Slack Of An Activity

The slack of an activity is the float of the activity.

Problem 1

The following details are available regarding a project:

| Activity | Predecessor Activity | Duration (Weeks) |
| --- | --- | --- |
| A | - | 12 |
| B | A | 7 |
| C | A | 11 |
| D | A | 8 |
| E | A | 6 |
| F | B | 10 |
| G | C | 9 |
| H | D, F | 14 |
| I | E, G | 13 |
| J | H, I | 16 |

Determine the earliest and latest times, the total float for each  activity, the critical activities and the project completion time.

279

Solution

With the given data, we construct the following network diagram  for the project.

A

1 2 12

3

B7 D 8

6 11

10 E

F

H

5

14

I

16

7 8

C G 4

6

9

Consider the paths, beginning with the start node and stopping  with the end node. There are four such paths for the given project. They  are as follows:

Path I

1 2 3 5 7 1

A

12

B 7

F

10

H 14

J

16

Time of the path = 12 + 7 + 10 + 14 + 16 = 59 weeks. Path II

1 2 5 7 8

A

12

D 8

H 14

J

16

Time of the path = 12 + 8 + 14 + 16 = 50 weeks.

Path III

1 2 6 7 8

A

12

E 6

I

13

J

16

280

Time of the path = 12 + 6 + 13 + 16 = 47 weeks. Path IV

A

C

G

I J

1 2 4 6 7 8

12

11

9

13 16

Time of the path = 12 + 11 + 9 + 13 + 16 = 61 weeks.

Compare the times for the four paths. Maximum of {51, 50, 47, 61} = 61.  We see that the maximum time of a path is 61 weeks.

Forward pass

Calculation of Earliest Expected Time of Occurrence of Events

| Node | Earliest Time of Occurrence of Node |
| --- | --- |
| 1 | 0 |
| 2 | Time for Node 1 + Time for Activity A = 0 + 12 = 12 |
| 3 | Time for Node 2 + Time for Activity B = 12 + 7 = 19 |
| 4 | Time for Node 2 + Time for Activity C = 12 + 11 = 23 |
| 5 6 | Max {Time for Node 2 + Time for Activity D, Time for Node 3 + Time for Activity F} = Max {12 + 8, 19 + 10} = Max {20, 29} = 29 Max {Time for Node 2 + Time for Activity E, Time for Node 4 + Time for Activity G} = Max {12 + 6, 23 + 9} = Max {18, 32} = 32 |
| 7 | Max {Time for Node 5 + Time for Activity H, Time for Node 6 + Time for Activity I} = Max {29 + 14, 32 + 13} = Max {43, 45} = 45 |
| 8 | Time for Node 7 + Time for Activity J = 45 + 16 = 61 |

281

Using the above values, we obtain the Earliest Start Times of the  activities as follows:

| Activity | Earliest Start Time (Weeks) |
| --- | --- |
| A | 0 |
| B | 12 |
| C | 12 |
| D | 12 |
| E | 12 |
| F | 19 |
| G | 23 |
| H | 29 |
| I | 32 |
| J | 45 |

Backward pass

Calculation of Latest Allowable Time of Occurrence of Events

| Node | Latest Allowable Time of Occurrence of Node |
| --- | --- |
| 8 | Maximum time of a path in the network = 61 |
| 7 | Time for Node 8 - Time for Activity J = 61 -16 = 45 |
| 6 | Time for Node 7 - Time for Activity I = 45 -13 = 32 |
| 5 | Time for Node 7 - Time for Activity H = 45 -14 = 31 |
| 4 | Time for Node 6 - Time for Activity G = 32 - 9 = 23 |
| 3 | Time for Node 5 - Time for Activity F = 31- 10 = 21 |

282

| 2 | Min {Time for Node 3 - Time for Activity B, Time for Node 4 - Time for Activity C, Time for Node 5 - Time for Activity D, Time for Node 6 - Time for Activity E} = Min {21 - 7, 23 - 11, 31 - 8, 32 - 6} = Min {14, 12, 23, 26} = 12 |
| --- | --- |
| 1 | Time for Node 2 - Time for Activity A = 12- 12 = 0 |

Using the above values, we obtain the Latest Finish Times of the  activities as follows:

| Activity | Latest Finish Time (Weeks) |
| --- | --- |
| J | 61 |
| I | 45 |
| H | 45 |
| G | 32 |
| F | 31 |
| E | 32 |
| D | 31 |
| C | 23 |
| B | 21 |
| A | 12 |

283

Calculation of Total Float for each activity:

| Activity | Duration (Weeks) | Earliest Start Time | Earliest Finish Time | Latest Start Time | Latest Finish Time | Total Float = Latest Finish Time - Earliest Finish Time |
| --- | --- | --- | --- | --- | --- | --- |
| A | 12 | 0 | 12 | 0 | 12 | 0 |
| B | 7 | 12 | 19 | 14 | 21 | 2 |
| C | 11 | 12 | 23 | 12 | 23 | 0 |
| D | 8 | 12 | 20 | 23 | 31 | 11 |
| E | 6 | 12 | 18 | 26 | 32 | 14 |
| F | 10 | 19 | 29 | 21 | 31 | 2 |
| G | 9 | 23 | 32 | 23 | 32 | 0 |
| H | 14 | 29 | 43 | 31 | 45 | 2 |
| I | 13 | 32 | 45 | 32 | 45 | 0 |
| J | 16 | 45 | 61 | 45 | 61 | 0 |

The activities with total float = 0 are A, C, G, I and J. They are the  critical activities.

Project completion time = 61 weeks.

Problem 2

The following are the details of the activities in a project:

| Activity | Predecessor Activity | Duration (Weeks) |
| --- | --- | --- |
| A | - | 15 |
| B | A | 17 |
| C | A | 21 |

284

| D | B | 19 |
| --- | --- | --- |
| E | B | 22 |
| F | C, D | 18 |
| G | E, F | 15 |

Calculate the earliest and latest times, the total float for each  activity and the project completion time.

Solution

The following network diagram is obtained for the given project.

A

1 2 15

B C

3

17 D 19 21

4

F

G

15

18

5 6

Consider the paths, beginning with the start node and stopping  with the end node. There are three such paths for the given project. They  are as follows:

Path I

1 2 3 5 6

A

15

B

17

E

22

G

15

Time of the path = 15 + 17 + 22 + 15 = 69 weeks.

Path II

1 2 3 4 5 6

A

15

B

17

D

19

F G 18 15

285

Time of the path = 15 + 17 + 19 + 18 + 15 = 84 weeks. Path III

1 2 4 5 6

A

15

C

21

F

18

G

15

Time of the path = 15 + 21 + 18 + 15 = 69 weeks.

Compare the times for the three paths. Maximum of {69, 84, 69} = 84. We  see that the maximum time of a path is 84 weeks.

Forward pass

Calculation of Earliest Time of Occurrence of Events

| Node | Earliest Time of Occurrence of Node |
| --- | --- |
| 1 | 0 |
| 2 | Time for Node 1 + Time for Activity A = 0 + 15 = 15 |
| 3 | Time for Node 2 + Time for Activity B = 15 + 17 = 32 |
| 4 | Max {Time for Node 2 + Time for Activity C, Time for Node 3 + Time for Activity D} = Max {15 + 21, 32 + 19} = Max {36, 51} = 51 |
| 5 | Max {Time for Node 3 + Time for Activity E, Time for Node 4 + Time for Activity F} = Max {32 + 22, 51 + 18} = Max {54, 69} = 69 |
| 6 | Time for Node 5 + Time for Activity G = 69 + 15 = 84 |

286

Calculation of Earliest Time for Activities

| Activity | Earliest Start Time (Weeks) |
| --- | --- |
| A | 0 |
| B | 15 |
| C | 15 |
| D | 32 |
| E | 32 |
| F | 51 |
| G | 69 |

Backward pass

Calculation of the Latest Allowable Time of Occurrence of Events

| Node | Latest Allowable Time of Occurrence of Node |
| --- | --- |
| 6 | Maximum time of a path in the network = 84 |
| 5 | Time for Node 6 - Time for Activity G = 84 -15 = 69 |
| 4 | Time for Node 5 - Time for Activity F = 69 - 18 = 51 |
| 3 | Min {Time for Node 4 - Time for Activity D, Time for Node 5 - Time for Activity E} = Min {51 - 19, 69 - 22} = Min {32, 47} = 32 |
| 2 | Min {Time for Node 3 - Time for Activity B, Time for Node 4 - Time for Activity C} = Min {32 - 17, 51 - 21} = Min {15, 30} = 15 |
| 1 | Time for Node 2 - Time for Activity A = 15 - 15 = 0 |

287

Calculation of the Latest Finish Times of the activities

| Activity | Latest Finish Time (Weeks) |
| --- | --- |
| G | 84 |
| F | 69 |
| E | 69 |
| D | 51 |
| C | 51 |
| B | 32 |
| A | 15 |

Calculation of Total Float for each activity:

| Activity | Duration (Weeks) | Earliest Start Time | Earliest Finish Time | Latest Start Time | Latest Finish Time | Total Float = Latest Finish Time - Earliest Finish Time |
| --- | --- | --- | --- | --- | --- | --- |
| A | 15 | 0 | 15 | 0 | 15 | 0 |
| B | 17 | 15 | 32 | 15 | 32 | 0 |
| C | 21 | 15 | 36 | 30 | 51 | 15 |
| D | 19 | 32 | 51 | 32 | 51 | 0 |
| E | 22 | 32 | 54 | 47 | 69 | 15 |
| F | 18 | 51 | 69 | 51 | 69 | 0 |
| G | 15 | 69 | 84 | 69 | 84 | 0 |

288

The activities with total float = 0 are A, B, D, F and G. They are the  critical activities.

Project completion time = 84 weeks.

Problem 3

Consider a project with the following details:

| Name of Activity | Predecessor Activity | Duration (Weeks) |
| --- | --- | --- |
| A | - | 8 |
| B | A | 13 |
| C | A | 9 |
| D | A | 12 |
| E | B | 14 |
| F | B | 8 |
| G | D | 7 |
| H | C, F, G | 12 |
| I | C, F, G | 9 |
| J | E, H | 10 |
| K | I, J | 7 |

Determine the earliest and latest times, the total float for each  activity, the critical activities, the slacks of the events and the project  completion time.

289

Solution

The following network diagram is got for the given project:

B

13

A

3

C

E

14

8

F

6

H1210 J

I

K

1 2 5

7 8

8

Path I

A

12

D

B

9

4

9

G

7

E

7

J K

1 2 3 6 7 8

8

13

14

10 7

Time of the path = 8 + 13 + 14 + 10 + 7 = 52 weeks.

Path II

1 2 3 5 6 7 8

A 8

B

13

H J K

F

8

12 10 7

Time of the path = 8 + 13 + 8 + 12 + 10 + 7 = 58 weeks. Path III

A

B

F

I K

1 2 3 5 7 8

8

3

8

9 7

Time of the path = 8 + 13 + 8 + 9 + 7 = 45 weeks.

290

Path IV A

C

H

J K

2 5 8 1 6 7

8

9

12

5

10 7

Time of the path = 8 + 9 + 12 + 10 + 7 = 46 weeks. Path V

A

C

I

5 7

K

1 8

2

8

9

9

7

5

6

Time of the path = 8 + 9 + 9 + 7 = 33 weeks.

Path VI

A

D

G

H

J

K

1 2 4 5 6 7 8

8

12

7

12

10

7

Time of the path = 8 + 12 + 7 + 12 + 10 + 7 = 56 weeks. Path VII

A

D

G

I K

1 2 4 5 7 8

8

12

7

9 7

Time of the path = 8 + 12 + 7 + 9 + 7 = 43 weeks.

Compare the times for the three paths. Maximum of {52, 58, 45, 46, 33, 56,  43} = 58.

We see that the maximum time of a path is 58 weeks.

291

Forward pass

Calculation of Earliest Time of Occurrence of Events

| Node | Earliest Time of Occurrence of Node |
| --- | --- |
| 1 | 0 |
| 2 | Time for Node 1 + Time for Activity A = 0 + 8 = 8 |
| 3 | Time for Node 2 + Time for Activity B = 8 + 13 = 21 |
| 4 | Time for Node 2 + Time for Activity D = 8+ 12 = 20 |
| 5 | Max {Time for Node 2 + Time for Activity C, Time for Node 3 + Time for Activity F, Time for Node 4 + Time for Activity G} = Max { 8 + 9, 21 + 8 , 20 + 7 } = Max {17, 29, 27} = 29 |
| 6 | Max {Time for Node 3 + Time for Activity E, Time for Node 5 + Time for Activity H} = Max {21 + 14 , 29 + 12} = Max {35, 41} = 41 |
| 7 | Max {Time for Node 5 + Time for Activity I, Time for Node 6 + Time for Activity J} = Max {29 + 9, 41 + 10} = Max {38, 51} = 51 |
| 8 | Time for Node 7 + Time for Activity J = 51+ 7 = 58 |

Earliest Start Times of the activities

| Activity | Earliest Start Time (Weeks) |
| --- | --- |
| A | 0 |
| B | 8 |

292

| C | 8 |
| --- | --- |
| D | 8 |
| E | 21 |
| F | 21 |
| G | 20 |
| H | 29 |
| I | 29 |
| J | 41 |
| K | 51 |

Backward pass

Calculation of Latest Allowable Time of Occurrence of Events

| Node | Latest Allowable Time of Occurrence of Node |
| --- | --- |
| 8 | Maximum time of a path in the network = 58 |
| 7 | Time for Node 8 - Time for Activity K = 58 -7 = 51 |
| 6 | Time for Node 7 - Time for Activity J = 51 -10 = 41 |
| 5 | Min {Time for Node 6 - Time for Activity H, Time for Node 7 - Time for Activity I} = Min {41 - 12, 51 - 9} = Min {29, 42} = 29 |
| 4 | Time for Node 5 - Time for Activity G = 29 - 7 = 22 |
| 3 | Min {Time for Node 5 - Time for Activity F, Time for Node 6 - Time for Activity E} = Min {29 - 8, 41 - 14} = Min {21, 27} = 21 |

293

| 2 | Min {Time for Node 3 - Time for Activity B, Time for Node 4 - Time for Activity D, = Min {21 - 13, 22 - 12, 29 - 9} = Min {8, 10, 20} = 8 |
| --- | --- |
| 1 | Time for Node 2 - Time for Activity A = 8 - 8 = 0 |

Latest Finish Times of the activities

| Activity | Latest Finish Time (Weeks) |
| --- | --- |
| K | 58 |
| J | 51 |
| I | 51 |
| H | 41 |
| G | 29 |
| F | 29 |
| E | 41 |
| D | 22 |
| C | 29 |
| B | 21 |
| A | 8 |

Calculation of Total Float for each activity:

294

| Activity | Duration (Weeks) | Earliest Start Time | Earliest Finish Time | Latest Start Time | Latest Finish Time | Total Float = Latest Finish Time - Earliest Finish Time |
| --- | --- | --- | --- | --- | --- | --- |
| A | 8 | 0 | 8 | 0 | 8 | 0 |
| B | 13 | 8 | 21 | 8 | 21 | 0 |
| C | 9 | 8 | 17 | 20 | 29 | 12 |
| D | 12 | 8 | 20 | 10 | 22 | 2 |
| E | 14 | 21 | 35 | 27 | 41 | 6 |
| F | 8 | 21 | 29 | 21 | 29 | 0 |
| G | 7 | 20 | 27 | 22 | 29 | 2 |
| H | 12 | 29 | 41 | 29 | 41 | 0 |
| I | 9 | 29 | 38 | 42 | 51 | 13 |
| J | 10 | 41 | 51 | 41 | 51 | 0 |
| K | 7 | 51 | 58 | 51 | 58 | 0 |

The activities with total float = 0 are A, B, F, H, J and K. They are the  critical activities.

Project completion time = 58 weeks.

Calculation of slacks of the events

Slack of an event = Latest Allowable Time of Occurrence of the  event - Earliest Expected Time of Occurrence of that event.

295

| Event (Node) | Earliest Expected Time of Occurrence of Event | Latest Allowable Time of Occurrence of Event | Slack of the Event |
| --- | --- | --- | --- |
| 1 | 0 | 0 | 0 |
| 2 | 8 | 8 | 0 |
| 3 | 21 | 21 | 0 |
| 4 | 20 | 22 | 2 |
| 5 | 29 | 29 | 0 |
| 6 | 41 | 41 | 0 |
| 7 | 51 | 51 | 0 |
| 8 | 58 | 58 | 0 |

Interpretation

On the basis of the slacks of the events, it is concluded that the  occurrence of event 4 may be delayed upto a maximum period of 2 weeks  while no other event cannot be delayed.

Questions

1. Explain the terms: The earliest and latest times of the activities of a  project.

2. Explain the procedure to find the earliest expected time of an event. 3. Explain the procedure to find the latest allowable time of an event. 4. What is meant by the slack of an activity? How will you determine it?  5. Consider the project with the following details:

296

| activity | Duration (weeks) |
| --- | --- |
| 1 2 | 1 |
| 2 3 | 3 |
| 2 4 | 7 |
| 3 4 | 5 |
| 3 5 | 8 |
| 4 5 | 4 |
| 5 6 | 1 |

Determine the earliest and the latest times of the activities. Calculate  the total float for each activity and the slacks of the events.

****

297

Lesson 7 - Crashing Of A Project

Lesson Outline

ӹ The Idea Of Crashing Of A Project

ӹ The Criterion Of Selection Of An Activity For Crashing ӹ Numerical Problems

Learning Objectives

After reading this lesson you should be able to

ӹ understand the concept of crashing of a project

ӹ choose an activity for crashing

ӹ work out numerical problems

The Meaning Of Crashing

The process of shortening the time to complete a project is called  crashing and is usually achieved by putting into service additional labour  or machines to one activity or more activities. Crashing involves more  costs. A project manager would like to speed up a project by spending as  minimum extra cost as possible. Project crashing seeks to minimize the  extra cost for completion of a project before the stipulated time.

Steps In Project Crashing

Assumption: It is assumed that there is a linear relationship between time  and cost.

Let us consider project crashing by the critical path method. The  following four-step procedure is adopted.

298

Step 1

Find the critical path with the normal times and normal costs for  the activities and identify the critical activities.

Step 2

Find out the crash cost per unit time for each activity in the network.  This is calculated by means of the following formula.

Crash t cos Crash t Normal t cos cos

− = −

Time period Normal time Crash time

Activity Cost

Crash Cost Normal Cost

|  | Crash time & Cost |
| --- | --- |

Normal time & Cost

Activity Time

Step 3

Crash Time Normal Time

Select an activity for crashing. The criteria for the selection is as

follows:

Select the activity on the critical path with the smallest crash cost  per unit time. Crash this activity to the maximum units of time as may be  permissible by the given data.

Crashing an activity requires extra amount to be spent. However,  even if the company is prepared to spend extra money, the activity time  cannot be reduced beyond a certain limit in view of several other factors.

299

In step 1, we have to note that reducing the time of on activity along the  critical path alone will reduce the completion time of a project. Because of  this reason, we select an activity along the critical path for crashing. In step 3, we have to consider the following question:

If we want to reduce the project completion time by one unit, which  critical activity will involve the least additional cost?

On the basis of the least additional cost, a critical activity is chosen  for crashing. If there is a tie between two critical activities, the tie can be  resolved arbitrarily.

Step 4

After crashing an activity, find out which is the critical path with  the changed conditions. Sometimes, a reduction in the time of an activity  in the critical path may cause a non-critical path to become critical. If the  critical path with which we started is still the longest path, then go to Step  3. Otherwise, determine the new critical path and then go to Step 3.

Problem 1

A project has activities with the following normal and crash times  and cost: .

| Activity | Predecessor Activity | Normal Time (Weeks) | Crash Time (Weeks) | Normal Cost (Rs.) | Crash Cost (Rs.) |
| --- | --- | --- | --- | --- | --- |
| A | - | 4 | 3 | 8,000 | 9,000 |
| B | A | 5 | 3 | 16,000 | 20,000 |
| C | A | 4 | 3 | 12,000 | 13,000 |
| D | B | 6 | 5 | 34,000 | 35,000 |
| E | C | 6 | 4 | 42,000 | 44,000 |
| F | D | 5 | 4 | 16,000 | 16,500 |
| G | E | 7 | 4 | 66,000 | 72,000 |
| H | G | 4 | 3 | 2,000 | 5,000 |

300

Determine a crashing scheme for the above project so that the total  project time is reduced by 3 weeks.

Solution

We have the following network diagram for the given project with  normal costs:

C

3

E

5

G

7

4

6

7 H

4

A

1 2 4

4

5

B

3

4

F

8 5

5 D6

4

6

4

Beginning from the Start Node and terminating with the End Node, there  are two paths for the network as detailed below:

Path I

1 2 5 7 8

A 4

B 5

D 6

F 5

The time for the path = 4 + 5 + 6 + 5 = 20 weeks.

Path II

1 2 3 5 7 8

A 4

B 5

D 6

F F 5 5

The time for the path = 4 + 4 + 6 + 7 + 4 = 25 weeks.

Maximum of {20, 25} = 25.

Therefore Path II is the critical path and the critical activities are A,  C, E, G and H. The non-critical activities are B, D and F.

301

Given that the normal time of activity A is 4 weeks while its crash  time is 3 weeks. Hence the time of this activity can be reduced by one  week if the management is prepared to spend an additional amount.  However, the time cannot be reduced by more than one week even if the  management may be prepared to spend more money. The normal cost of  this activity is Rs. 8,000 whereas the crash cost is Rs. 9,000. From this, we  see that crashing of activity A by one week will cost the management an  extra amount of Rs. 1,000. In a similar fashion, we can work out the crash  cost per unit time for the other activities also. The results are provided in  the following table.

| Activity | Normal Time | Crash Time | Normal Cost | Crash Cost | Crash cost - Normal Cost | Normal Time - Crash Time | Crash Cost per unit time |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | 4 | 3 | 8,000 | 9,000 | 1,000 | 1 | 1,000 |
| B | 5 | 3 | 16,000 | 20,000 | 4,000 | 2 | 2,000 |
| C | 4 | 3 | 12,000 | 13,000 | 1,000 | 1 | 1,000 |
| D | 6 | 5 | 34,000 | 35,000 | 1,000 | 1 | 1,000 |
| E | 6 | 4 | 42,000 | 44,000 | 2,000 | 2 | 1,000 |
| F | 5 | 4 | 16,000 | 16,500 | 500 | 1 | 500 |
| G | 7 | 4 | 66,000 | 72,000 | 6,000 | 1 | 6,000 |
| H | 4 | 3 | 2,000 | 5,000 | 3,000 | 1 | 3,000 |

A non-critical activity can be delayed without delaying the  execution of the whole project. But, if a critical activity is delayed, it will  delay the whole project. Because of this reason, we have to select a critical  activity for crashing. Here we have to choose one of the activities A, C, E,  G and H The crash cost per unit time works out as follows:

302

Rs. 1,000 for A; Rs. 1,000 for C; Rs. 1,000 for E; Rs. 6,000 for G; Rs. 3,000  for H.

The maximum among them is Rs. 1,000. So we have to choose an  activity with Rs.1,000 as the crash cost per unit time. However, there  is a tie among A, C and E. The tie can be resolved arbitrarily. Let us select  A for crashing. We reduce the time of A by one week by spending an extra  amount of Rs. 1,000.

After this step, we have the following network with the revised  times for the activities:

3

E

5

G

7

C

4

6

7 H

4

A

1 2 3

4

5

B

3

4

F

8 5

5 D6

4

6

4

The revised time for Path I = 3 + 5 + 6 + 5 = 19 weeks.

The time for Path II = 3 + 4 + 6 + 7 + 4 = 24 weeks.

Maximum of {19, 24} = 24.

Therefore Path II is the critical path and the critical activities are  A, C, E, G and H. However, the time for A cannot be reduced further.  Therefore, we have to consider C, E, G and H for crashing. Among them,  C and E have the least crash cost per unit time. The tie between C and E  can be resolved arbitrarily. Suppose we reduce the time of C by one week  with an extra cost of Rs. 1,000.

After this step, we have the following network with the revised times for  the activities:

3

E

5

G

7

C

4

6

7 H

4

A

1 2 3

3

5

B

3

4

F

8 5

5 D6

4

6

4

303

The time for Path I = 3 + 5 + 6 + 5 = 19 weeks.

The time for Path II = 3 + 3 + 6 + 7 + 4 = 23 weeks.

Maximum of {19, 23} = 23.

Therefore Path II is the critical path and the critical activities are  A, C, E, G and H. Now the time for A or C cannot be reduced further.  Therefore, we have to consider E, G and H for crashing. Among them, E  has the least crash cost per unit time. Hence we reduce the time of E by one  week with an extra cost of Rs. 1,000.

By the given condition, we have to reduce the project time by 3  weeks. Since this has been accomplished, we stop with this step.

Result: We have arrived at the following crashing scheme for the given  project:

Reduce the time of A, C and E by one week each.

Project time after crashing is 22 weeks.

Extra amount required = 1,000 + 1,000 + 1,000 = Rs. 3,000. Problem 2

The management of a company is interested in crashing of the  following project by spending an additional amount not exceeding Rs.  2,000. Suggest how this can be accomplished.

| Activity | Predecessor Activity | Normal Time (Weeks) | Crash Time (Weeks) | Normal Cost (Rs.) | Crash Cost (Rs.) |
| --- | --- | --- | --- | --- | --- |
| A | - | 7 | 6 | 15,000 | 18,000 |
| B | A | 12 | 9 | 11,000 | 14,000 |
| C | A | 22 | 21 | 18,500 | 19,000 |
| D | B | 11 | 10 | 8,000 | 9,000 |
| E | C, D | 6 | 5 | 4,000 | 4,500 |

304

Solution

We have the following network diagram for the given project with  normal costs:

3

B12D

A

C

11 E

1 2 4 5

7

22

6

There are two paths for this project as detailed below: Path I

A

B

D

E

1 2 3 4 5

7

12

11

6

The time for the path = 7 + 12 + 11 + 6 = 36 weeks.

Path II

1 2 4 5

A7

C

22

E 6

The time for the path = 7 + 22 + 6 = 35 weeks.

Maximum of {36, 35} = 36.

Therefore Path I is the critical path and the critical activities are A,  B, D and E. The non-critical activity is C.

The crash cost per unit time for the activities in the project are provided  in the following table.

305

| Activity | Normal | Crash Time | Normal Cost | Crash Cost | Crash cost - Normal Cost | Normal Time - Crash Time | Crash Cost per unit time |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | 7 | 6 | 15,000 | 18,000 | 3,000 | 1 | 3,000 |
| B | 12 | 9 | 11,000 | 14,000 | 3,000 | 3 | 1,000 |
| C | 22 | 21 | 18,500 | 19,000 | 500 | 1 | 500 |
| D | 11 | 10 | 8,000 | 9,000 | 1,000 | 1 | 1,000 |
| E | 6 | 5 | 4,000 | 4,500 | 500 | 1 | 500 |

We have to choose one of the activities A, B, D and E for crashing.  The crash cost per unit time is as follows:

Rs. 3,000 for A; Rs. 1,000 for B; Rs. 1,000 for D; Rs. 500 for E.

The least among them is Rs. 500. So we have to choose the activity  E for crashing. We reduce the time of E by one week by spending an extra  amount of Rs. 500.

After this step, we have the following network with the revised  times for the activities:

B12D

3

A

C

11 E

1 2 4 5

7

22

5

The revised time for Path I = 7 + 12 + 11 + 5 = 35 weeks. The time for Path II = 7 + 22 + 5 = 34 weeks. Maximum of {35, 34} = 35.

306

Therefore Path I is the critical path and the critical activities are A,  B, D and E. The non-critical activity is C.

The time of E cannot be reduced further. So we cannot select it  for crashing. Next B and have the smallest crash cost per unit time. Let us  select B for crashing. Let us reduce the time of E by one week at an extra  cost of Rs. 1,000.

After this step, we have the following network with the revised times for  the activities:

B11D

3

A

C

11 E

1 2 4 5

7

22

5

The revised time for Path I = 7 + 11 + 11 + 5 = 34 weeks. The time for Path II = 7 + 22 + 5 = 34 weeks.

Maximum of {34, 34} = 34.

Since both paths have equal times, both are critical paths. So, we  can choose an activity for crashing from either of them depending on the  least crash cost per unit time. In path I, the activities are A, B, D and E. In  path II, the activities are A, C and E.

The crash cost per unit time is the least for activity C. So we select  C for crashing. Reduce the time of C by one week at an extra cost of Rs.  500.

By the given condition, the extra amount cannot exceed Rs. 2,000.  Since this state has been met, we stop with this step.

Result: The following crashing scheme is suggested for the given project: Reduce the time of E, B and C by one week each.

Project time after crashing is 33 weeks.

Extra amount required = 500 + 1,000 + 500 = Rs. 2,000.

307

Problem 3

The manager of a company wants to apply crashing for the following  project by spending an additional amount not exceeding Rs. 2,000. Offer  your suggestion to the manager.

| Activity | Predecessor Activity | Normal Time (Weeks) | Crash Time (Weeks) | Normal Cost (Rs.) | Crash Cost (Rs.) |
| --- | --- | --- | --- | --- | --- |
| A | - | 20 | 19 | 8,000 | 10,000 |
| B | - | 15 | 14 | 16,000 | 19,000 |
| C | A | 22 | 20 | 13,000 | 14,000 |
| D | A | 17 | 15 | 7,500 | 9,000 |
| E | B | 19 | 18 | 4,000 | 5,000 |
| F | C | 28 | 27 | 3,000 | 4,000 |
| G | D, E | 25 | 24 | 12,000 | 13,000 |

Solution

We have the following network diagram for the given project with  normal costs:

3

C

5

A 22

F

1

20

B

15

D 28

17

7

G

2

E

19

4

25

308

There are three paths for this project as detailed below:

Path I

1 2 4 6

A C F

20 22 28

The time for the path = 20 + 22 + 28= 70 weeks.

Path II

A D G

1 2 5 6

20 17 25

The time for the path = 20 + 17 + 25= 62 weeks.

Path III

1 3 5 6

B E G

15 19 25

The time for the path = 15+19 +25 = 69 weeks.

Maximum of {70, 62, 69} = 70.

Therefore Path I is the critical path and the critical activities are A,  C and F. The non-critical activities are B, D, E and G.

The crash cost per unit time for the activities in the project are  provided in the following table

309

| Activity | Normal Time | Crash Time | Normal Cost | Crash Cost | Crash cost - Normal Cost | Normal Time - Crash Time | Crash Cost per unit time |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | 20 | 19 | 8,000 | 10,000 | 2,000 | 1 | 2,000 |
| B | 15 | 14 | 16,000 | 19,000 | 3,000 | 1 | 3,000 |
| C | 22 | 20 | 13,000 | 14,000 | 1,000 | 2 | 500 |
| D | 17 | 15 | 7,500 | 9,000 | 1,500 | 2 | 750 |
| E | 19 | 18 | 4,000 | 5,000 | 1,000 | 1 | 1,000 |
| F | 28 | 27 | 3,000 | 4,000 | 1,000 | 1 | 1,000 |
| G | 25 | 24 | 12,000 | 13,000 | 1,000 | 1 | 1,000 |

We have to choose one of the activities A, C and F for crashing. The  crash cost per unit time is as follows:

Rs. 2,000 for A; Rs. 500 for C; Rs. 1,000 for F.

The least among them is Rs. 500. So we have to choose the activity  C for crashing. We reduce the time of C by one week by spending an extra  amount of Rs. 500.

After this step, we have the following network with the revised times for  the activities:

A

3

C

21

5

F

1

20

B

15

D 28

17

7

G

2

E

19

4

25

310

The revised time for Path I = 20 + 21 + 28= 69 weeks.

The time for Path II = 20 + 17 + 25= 62 weeks.

The time for Path III = 15+19 +25 = 69 weeks.

Maximum of {69, 62, 69} = 69.

Since paths I and III have equal times, both are critical paths. So,  we can choose an activity for crashing from either of them depending on  the least crash cost per unit time.

In path I, the activities are A, C and F. In path III, the activities are  B, E and G.

The crash cost per unit time is the least for activity C. So we select  C for crashing. Reduce the time of C by one week at an extra cost of Rs.  500.

After this step, we have the following network with the revised times for  the activities:

A

3

C

20

5

F

1

20 B

D 28

17

7

G

15

2

E

19

4

25

The revised time for Path I = 20 + 20 + 28= 68 weeks.

The time for Path II = 20 + 17 + 25= 62 weeks.

The time for Path III = 15+19 +25 = 69 weeks.

Maximum of {68, 62, 69} = 69.

Therefore path III is the critical activities. Hence we have to select  an activity from Path III for crashing. We see that the crash cost per unit  time is as follows:

Rs. 3,000 for B; Rs. 1,000 for E; Rs. 1,000 for G.

311

The least among them is Rs. 1,000. So we can select either E or G  for crashing. Let us select E for crashing. We reduce the time of E by one  week by spending an extra amount of Rs. 1,000.

By the given condition, the extra amount cannot exceed Rs. 2,000.  Since this condition has been reached, we stop with this step.

Result: The following crashing scheme is suggested for the given project: Reduce the time of C by 2 weeks and that of E by one week.

Project time after crashing is 67 weeks.

Extra amount required = 2 x 500 + 1,000 = Rs. 2,000.

Questions

1. Explain the concept of crashing of a project.

2. Explain the criterion for selection of an activity for crashing. ****

312